## Promotion
DEV to PROD promotion checklist
REVIEW DRAFT. 20 Sep 2026. Based on current R009 policy. No promotion has been performed.
Review: choose Keep / Revise / Remove, edit wording or add table rows. Put proposed changes in Notes. All cells are editable.
Execute after approval: copy per release, filter When required, reuse valid evidence, and record one result per applicable row.
Done requires evidence. Reused requires a valid reference. N/A requires a reason. Resolve Blocked/Pending before Released.
Open only the source section needed for a triggered step. No full-app diff, repeated DEV suite or routine recipient audit.
Approval will make the revised checklist the execution scope; until then, current AGENTS/runbooks remain authoritative.
ID | Stage | When required | Activity and completion criterion | Status | Review decision | Notes / evidence / proposed wording | Source section
P01 | A Readiness | Always | Confirm the reserved Rnnn, included changes, dependencies and acceptance criteria. Mark each app Upgrade or Unchanged; identify SQL and external scope. | Not started | Review |  | AGENTS: tracking; Workflow A
P02 | A Readiness | Always | Read continuation, manifest, log and affected evidence; reuse completed checks. Preserve other tasks’ work. If readiness fixes require edits, record the starting Git commit, affected restorable app versions and applicable DB recovery first. | Not started | Review |  | AGENTS: working method; §4
P03 | A Readiness | Always | Confirm integrated DEV includes every release feature and prior PROD fix, with no unrelated unreleased configuration. Resolve scope/dependency conflicts before RC copy. | Not started | Review |  | Workflow A1–4
P04 | A Readiness | SQL changes | Verify immutable, ordered Flyway migrations and justified/approved new tables or columns. Confirm migration-chain, DEV migrate/validate and affected SQL tests passed from the intended candidate. | Not started | Review |  | Database: Each change 1–4
P05 | A Readiness | SQL / compatibility impact | Verify old/new apps, mixed OLTP/OLAP states and relevant offline/queued clients work with expanded SQL. Record migration locks/backfills, deployment order and any reviewed maintenance window. | Not started | Review |  | Recovery: Before promotion
P06 | A Readiness | New/changed guards or app IDs | Establish scheduled guards in DEV before RC copy. Use exact canonical DEV/PROD internal names. Guard all scheduled side effects and child calls; add the guard to existing per-row filters. Preserve intended states/schedules. | Not started | Review |  | Workflow: Scheduled guard 1–4
P07 | A Readiness | First use / invalidated guard proof | Prove guard behavior in server-side scheduling using deployed DEV and a harmless DEV-bound copy. Show allowed DEV and excluded copy; retire diagnostics. Later releases reuse valid runtime evidence. | Not started | Review |  | Workflow: Scheduled guard 5–7
P08 | A Readiness | Setup / changed notification routes | Verify DEV-only sources/links/delivery and affected external routes. For R009, preserve distinct Login Email, set DEV delivery Email to owner, exclude recorded actor by Partner ID, deduplicate nonblank addresses. Investigate unmapped actors. Reuse untouched routing evidence. | Not started | Review |  | AGENTS §2; DEV preparation
P09 | A Readiness | DEV not yet Deployed / replacement | After isolation and guards are ready, complete initial DEV deployment checks and mark apps Deployed. Already-Deployed apps need no repeat check or mode toggle. | Not started | Review |  | Workflow: App mode rules
P10 | A Readiness | Always; reuse valid results | Confirm integrated DEV tests cover changed behavior and consumers in the current GUI. Include relevant normal/boundary/retry/financial paths and SQL reconciliation. Rerun only invalidated checks; distinguish configuration, execution and delivery evidence. | Not started | Review |  | Workflow: Test selection
P11 | A Readiness | Always | Record both DEV apps’ final saved versions and zero editor warnings/errors, including pre-existing issues. Resolve defects; do not hide or waive the editor gate. | Not started | Review |  | Workflow A5; warning rules
P12 | A Readiness | Always | Reconcile concise scope/change record, DEV checkpoint and affected model overview/dictionary. State Ready, Conditional or Not ready with open checks. Record owner acceptance separately from deployment authority. | Not started | Review |  | Workflow A5; AGENTS §5–6
P13 | B Capture | App Upgrade scope | Confirm App Upgrade availability, ownership and copy prerequisites. Record existing PROD target IDs, app order, window and recovery approach. Avoid discovering eligibility after PROD changes. | Not started | Review |  | Workflow B2
P14 | B Capture | Always | Briefly freeze affected shared DEV edits. Pin tested app/SQL versions, implementation commit, scope revision, test references and recovery. Record unchanged companion apps explicitly. | Not started | Review |  | Workflow B1
P15 | B Capture | SQL changes | From the clean tested commit, run New-Release.ps1 before later DEV migrations advance. Retain original private manifest and publish sanitized hashes/target. Account for every pending migration and approved prerequisite. | Not started | Review |  | Database: Each change 5
P16 | B Capture | App Upgrade scope | Copy included integrated DEV definitions to MW-OLTP-Rnnn-RCk / MW-OLAP-Rnnn-RCk. Record complete internal names, UUIDs, versions, copy options and time. Do not copy DEV financial data to PROD. | Not started | Review |  | Workflow B3
P17 | B Capture | App Upgrade scope | Contain RC from creation: restricted access, no uncontrolled writes/delivery or external execution. Keep it DEV-bound with affected jobs paused if guard proof is missing. PROD-bound tests need scoped authority. | Not started | Review |  | Workflow: RC containment
P18 | B Capture | App Upgrade scope | Capture each corresponding PROD theme/branding separately; apply it after DEV-to-RC copy. Check exact saved colors and appearance, display name/icon. Preserve all four DEV/PROD themes; no DEV/RC branding leaks into PROD. | Not started | Review |  | Workflow B4
P19 | B Capture | Always | Confirm captures and migration pins are independent and reproducible, then release the DEV edit freeze. Later DEV work must not change this candidate or its validation baseline. | Not started | Review |  | Workflow B5
P20 | C PROD database | Before PROD writes / RC PROD effects | Confirm existing scoped owner authorization covers the package, SQL and RC production effects. Record approval reference; request only missing scope. No forced financial tests or notifications without their own coverage. | Not started | Review |  | Workflow C; AGENTS §1
P21 | C PROD database | Always | Verify actual PROD host/instance and app identities against inventory; record current SQL/app baseline and dependencies. For no-SQL releases record migrations N/A; do not create empty migrations. | Not started | Review |  | Workflow C
P22 | C PROD database | SQL changes / PROD DB writes | Establish a verified restorable PROD backup and recovery reference. Inspect expected pre-release schema versus live drift and Flyway history/checksums. Stop on unexplained drift; validate alone is insufficient. | Not started | Review |  | Database: Each change 6
P23 | C PROD database | SQL changes | Use the existing production Flyway runner from the pinned clean commit/original manifest: validate, migrate, validate. Include approval/backup references. Never repair, clean, edit checksums or skip migrations to conceal drift. | Not started | Review |  | Database: Each change 7
P24 | C PROD database | SQL changes | Confirm target history/schema/objects with relevant read-only SQL checks. Record pre-migration and post-migration versions. Compatible migrations must succeed before final RC PROD-source validation. | Not started | Review |  | Workflow C
P25 | D RC preparation | App Upgrade scope | Rebind and reconcile every RC table/view/source to PROD. Verify host, database, schema and object, plus auxiliary/file/internal sources. No DEV source remains in the production definition. | Not started | Review |  | Workflow D1
P26 | D RC preparation | App Upgrade scope | Set inter-app links to the actual PROD OLTP/OLAP pair, never DEV or RC companions. Verify saved mappings and navigation without submitting production actions. | Not started | Review |  | Workflow D2
P27 | D RC preparation | App Upgrade scope | Keep R009 shared recipient expressions and verify PROD Login Email schema/actor mapping prerequisites. RC reads PROD contact data. Restore only remaining documented legacy DEV overrides; never restore superseded email-based actor exclusion. | Not started | Review |  | AGENTS §6.2; Workflow D2
P28 | D RC preparation | Affected external assets / access | Verify/provision production templates, files, endpoints, access grants and integrations that App Upgrade does not transfer. Record external steps and destinations once, without secrets. | Not started | Review |  | Workflow: RC external dependencies
P29 | D RC preparation | App Upgrade scope | Verify copied scheduled guards retain exact canonical DEV/PROD names, exclude this RC and precede every scheduled business effect. Preserve intended enabled/retired states and schedules. Reuse valid first-use proof. | Not started | Review |  | Workflow: Scheduled guard
P30 | D RC preparation | App Upgrade scope | Save/reload and run current-editor data validation. Check source/Ref/security/type/permission integrity and affected generated metadata; resolve zero editor issues. Investigate unexpected copy/regeneration changes only. | Not started | Review |  | Workflow D3–4
P31 | D RC preparation | App Upgrade scope | Perform basic RC open/sync, access and affected-screen checks. Reuse DEV business tests; inspect/cancel forms. Record real limitations; no full suite, whole-app diff or forced production delivery. | Not started | Review |  | Workflow D3–4; RC containment
P32 | D RC preparation | New RC | With containment verified, complete initial RC Deployment Check, resolve findings and mark it Deployed. Do not toggle an already-Deployed app to rerun a check. | Not started | Review |  | Workflow: App mode rules
P33 | D RC preparation | App Upgrade scope | Freeze final deployed RC UUID/internal name/version, mappings/substitutions, guard evidence, tests and package revision in the manifest. Set ready-immutable only now. Later fixes require a new RC and affected retesting. | Not started | Review |  | Workflow D5
P34 | E App Upgrade | Always | Confirm owner acceptance and production authorization cover the final package, named RC revisions, SQL and remaining operational steps. Reuse valid prior authorization; a manifest entry is not approval. | Not started | Review |  | Workflow E1
P35 | E App Upgrade | App Upgrade scope | Record PROD pre-upgrade/restorable versions, IDs, SQL state, smoke baseline and ordered recovery plan. Ensure app-version retention covers the recovery window; preserve private recovery copies only if needed. | Not started | Review |  | Workflow E2; Recovery
P36 | E App Upgrade | Immediately before each upgrade | Confirm PROD has not changed from the accepted baseline and RC still has its frozen version. If PROD changed, integrate those changes into a new candidate and retest; do not overwrite intervening work. | Not started | Review |  | AGENTS §6.3; Workflow E1–3
P37 | E App Upgrade | Each included app | Run App Upgrade in the existing PROD target using the frozen RC’s full internal name. Verify target UUID and source version. Record source/target, timestamp and before/after versions; confirm success before dependent upgrades. | Not started | Review |  | Workflow E3–4
P38 | E App Upgrade | Operational pauses / external steps | Complete approved external cutover steps and reconcile temporary pauses in the planned order. Keep integrity triggers active and one scheduler per business job/environment. No manual recreation of app settings in PROD. | Not started | Review |  | Workflow E4; AGENTS §2
P39 | F PROD validation | App Upgrade scope | Verify upgrade provenance, resulting PROD version/Deployed state, PROD sources and necessary link/theme/access substitutions against the frozen RC/package. Use focused saved checks; never compare to later DEV. | Not started | Review |  | Workflow F1
P40 | F PROD validation | Always | Open/sync both PROD apps, check access and representative changed entry points/affected consumers. Inspect/cancel forms. Reuse DEV tests; use only separately authorized mutating actions or notification tests. | Not started | Review |  | Workflow F2
P41 | F PROD validation | Changed SQL / critical / external behavior | Run the selected read-only SQL reconciliation and targeted critical/external checks. Expand only for observed mismatches or concrete uncertainty. Configuration readback is not proof of execution/delivery. | Not started | Review |  | Workflow F2–3
P42 | F PROD validation | Changed recipient logic / identity prerequisites | Verify affected actor mapping and shared recipient rules against the frozen package. No routine recipient rewrite/audit for untouched routes. Resolve unknown actors before accepting affected notification tests. | Not started | Review |  | AGENTS §2, §6.4
P43 | F PROD validation | App Upgrade / scheduler impact | Confirm PROD is allowed and RC excluded by scheduled guards, intended states/schedules preserved and duplicate execution contained. At first introduction observe the next normal PROD run; later releases reuse valid proof. | Not started | Review |  | Workflow: Guard 5–7; F3
P44 | F PROD validation | Always | Record final app/Flyway versions, both PROD editors’ zero warnings/errors and smoke/SQL results. No fresh Deployment Check for already-Deployed PROD. Required missing checks mean verification incomplete, not Released. | Not started | Review |  | Workflow F3–4
P45 | G Documentation | Always | Reconcile a fresh recursive Documents inventory with the Documents tab/register. Add/classify new or moved files. Complete every document row with a disposition and evidence/reason; no uncatalogued, Pending or Blocked item at closure. | Not started | Review |  | Documentation checklist 2–6
P46 | G Documentation | Always | Reconcile manifest, release log/checklist, source mappings, approvals/tests, implementation/Flyway pins and DEV/RC/PROD versions. Update model overview/dictionary together when triggered; close only promoted differences and preserve later DEV. | Not started | Review |  | Workflow F5; Documentation checklist
P47 | G Documentation | Always | Run relevant document/model/link checks, inspect intended Git diff, preserve unrelated work and exclude secrets/private data/backups/dependencies. A documentation gap needs repair, not another deployment or repeated live tests. | Not started | Review |  | AGENTS §5; Documentation checklist 7
P48 | H Publication | Always | Prepare final outcome and intended tag in records. Commit/push sanitized evidence/docs to configured upstream. Create/push unique annotated Rnnn tag at the final evidence commit and verify remote branch/tag targets. Never move an existing tag. | Not started | Review |  | Workflow F6; AGENTS publication
P49 | H Publication | RC exists | Record RC recovery/retention window and continued containment without editing frozen definitions. Retire only under the recorded decision, preserving recoverable evidence/shared assets. No automatic RC deletion or DEV refresh. | Not started | Review |  | Recovery: RC retention; Workflow F7
P50 | H Publication | Always | Confirm validation, documentation and publication complete before final Released report. Give release outcome, versions, tag/evidence, rollback and limitations. Otherwise state the specific incomplete phase; repair publication without redeploying. | Not started | Review |  | Workflow F4–7
P51 | X Exceptions | Unlisted necessary work / required check unavailable | Record the concrete gap and its effect on the affected step. Continue independent work. Seek owner disposition for missing scope or checklist amendment; do not silently add unrelated gates or waive zero-editor-issue requirements. | Not started | Review |  | AGENTS working method; proposed checklist-use rule
P52 | X Exceptions | Deployment failure / uncertain result | Stop dependent steps and uncontrolled RC effects. Record actual SQL/apps/external state and first failure. Investigate before retrying; a timeout is not proof of failure and does not authorize financial replay. | Not started | Review |  | Recovery: Failure 1–2
P53 | X Exceptions | SQL succeeded; app upgrade incomplete | Keep compatible additive SQL if safe. Correct in controlled development, create a new RC and retest. Do not restore the database merely to remove a successful compatible migration. | Not started | Review |  | Recovery: Failure 3
P54 | X Exceptions | App rollback / forward recovery needed | Use recorded restorable versions in dependency order or an approved forward fix. Keep existing PROD IDs, preserve newer data and verify mixed-app compatibility. Recheck sources/links/themes/recipients, editors and affected runtime paths. | Not started | Review |  | Recovery: Failure 4–5
P55 | X Exceptions | Database recovery needed | Prefer a tested higher Flyway forward fix. Destructive backup/PITR recovery needs scoped approval, verified restore point, write pause and treatment of newer writes. Revalidate history/schema/access and affected consumers; app restore does not undo SQL or sent messages. | Not started | Review |  | Recovery: Failure 6
P56 | X Exceptions | Emergency manual PROD change | Require scoped approval and exact before/after/version evidence. Reconcile app changes into DEV/Git and SQL into reviewed migrations before the next candidate. Resume normal RC promotion; never make manual edits the default fallback. | Not started | Review |  | Recovery: Hotfix/emergency
P57 | X Exceptions | Rollback / hotfix / failed closure | Record actual partial/rolled-back/forward-fixed state and repair tracker, development differences and affected documentation. Reopen reversed differences, preserve history and publish evidence. A new hotfix gets the next Rnnn and normal controlled RC workflow. | Not started | Review |  | Recovery: Failure 7; Hotfix

## Documents
Promotion documentation closure
Every listed document receives its own disposition; update only affected content. Preserve dated evidence and later DEV work.
Always: Updated or Verified current. Conditional: update/verify when triggered, otherwise N/A with a reason.
Historical: Preserved history unless the historical document itself is explicitly in scope. Read only relevant sections.
Reconcile a fresh Documents inventory at closure. Add/classify new or moved paths; no missing or Pending/Blocked rows.
Use Review decision / Notes to propose changes now. Status remains Pending until an actual promotion is performed.
Source: Documents/Promotion_Documentation_Checklist.md at commit 5cecc67580a8a401c7dc8e4d8a147f119f161edf.
ID | Document (under Documents/) | Rule | Update trigger and required content | Disposition | Review decision | Notes / evidence / proposed wording
DOC-001 | Release_Tracker.md | Always | Status/dates, manifest and frozen RC identities/versions, implementation/Flyway pins, approval, PROD before/after, evidence/tag and recovery. Link completed checklist; Released requires all required rows and publication. | Pending | Review
DOC-002 | Environment_Inventory.md | Always | Final PROD app/SQL versions, existing IDs/Deployed modes and basic RC-to-PROD source/theme/link checks; DEV owner-only delivery-data baseline and shared recipient logic/identity prerequisites; legacy RC substitutions only where applicable; RC manifest/containment/retention link. Label unchanged/unobserved components accurately; preserve later DEV. RC copy/rebind triggers routing checks; ordinary DEV edits don't. | Pending | Review
DOC-003 | Development_Changes.md | Always | Integrated DEV checkpoint, source RC/manifest and explicit promoted/closed state for every release-scope difference, PROD versions/date and basic validation/log links; no mandatory all-property readback. Preserve later DEV-only work; supersede stale blockers and retain labeled history. | Pending | Review
DOC-004 | AppSheet_Data_Model_Overview.md | Conditional | Model/business-rule/ownership/calculation/relationship/slice/availability changes, including formula-only changes: update affected production summary and resolve this release's DEV annotations, paired with the dictionary. | Pending | Review
DOC-005 | AppSheet_Data_Dictionary.xlsx | Conditional | Same model triggers as DOC-004: exact affected production rows, Dev Differences, expressions, availability and SQL inventory. Check changed values/layout and preserve other sheets/later DEV work. Formula changes count without a migration. | Pending | Review
DOC-006 | OLTP_Business_Processes.md | Conditional | Changed operational steps, actions/approvals, posting/retry behavior or boundaries represented here: update affected narrative/evidence with its diagram. Optimization with unchanged business behavior need not redraw workflows. | Pending | Review
DOC-007 | OLTP_Business_Processes.drawio | Conditional | Changed process/node/decision/flow represented in DOC-006: edit affected pages and check narrative agreement. Diagram edits do not prove new lifecycle tests. | Pending | Review
DOC-008 | Loan_Business_Ecosystem.md | Conditional | Changed systems, ownership, integration/data flows, access/recovery or service relationships represented here: update affected statements/evidence with its diagram; preserve other projects' boundaries. | Pending | Review
DOC-009 | Loan_Business_Ecosystem.drawio | Conditional | Changed architecture/services/flows in DOC-008: reconcile affected nodes/connections. Version-only or internal formula changes need no redraw. | Pending | Review
DOC-010 | Daily_Loan_Analysis_Automation.md | Conditional | Changed analysis/export contract, workbook fields/grain, source, schedule, recipients, enablement or pilot acceptance. Distinguish configuration from actual execution/delivery; unrelated bots do not trigger a pilot audit. | Pending | Review
DOC-011 | Solution_Design.md | Conditional | Changed ownership, prototype/business design principles, reporting boundaries or Looker page order. Routine implementation/version updates do not change policy. | Pending | Review
DOC-012 | README.md | Conditional | New/renamed/retired documents, changed authority/purpose or status made stale by the release. Prefer links to authoritative records over duplicate release/version summaries. | Pending | Review
DOC-013 | Release_Workflow.md | Conditional | Changed release/test/approval/promotion/closure methodology or a proven procedural correction; routine releases do not add their history here. | Pending | Review
DOC-014 | Development_Environment_Preparation.md | Conditional | Changed setup/isolation/parity procedure or canonical references. Ordinary versions/unchanged routes require neither a rewrite nor full preparation rerun. | Pending | Review
DOC-015 | Development_Refresh_Runbook.md | Conditional | Changed refresh/recovery/copy/restore procedure or compatibility assumptions. A routine promotion does not request a DEV refresh. | Pending | Review
DOC-016 | Core_Payment_SQL_Migration_Plan.md | Historical | Dated phases 1–3 plan/checkpoint: preserve decisions. Current behavior belongs in model/workflow references and release log. Revise this plan only when the plan itself is expressly in scope; old pending status is not current. | Pending | Review
DOC-017 | Universal_Payments_Clone_Migration_Runbook.md | Historical | Earlier AppSheet-native migration procedure; preserve it, not a current PostgreSQL promotion procedure. | Pending | Review
DOC-018 | AppSheet_Data_Model_History.md | Historical | Archived model; preserve dated claims. Current updates go to DOC-004/005. | Pending | Review
DOC-019 | history/AppSheet_Data_Dictionary_before_reconciliation_2026-09-15.xlsx | Historical | Preserve this historical workbook byte-for-byte; never update it instead of the current dictionary. | Pending | Review
DOC-020 | Promotion_Documentation_Checklist.md | Conditional | Classify new/moved Documents paths and adjust triggers when documentation ownership changes. No routine release history belongs here. | Pending | Review
DOC-021 | Release_Recovery_Runbook.md | Conditional | Changed app rollback, SQL forward-fix/recovery, hotfix reconciliation or RC retention procedure. Routine release-specific recovery points belong in its manifest/log, not this runbook. | Pending | Review